## Slide 1
GO-TO-MARKET PLAN
FieldSense 200 Series Launch Campaign Plan
Marketing · Nadia · February 10, 2026

## Slide 2
The Launch Plan on One Page
Apr 7
Public launch
product page soft-live April 4
$92K
Campaign budget requested
April through June
180
Units sold in the first 90 days
from 250 sellable
$750K
New qualified pipeline
sourced in 90 days
Premium positioning on accuracy under vibration; no launch discount
Email, paid search, trade press, and one regional trade show
Sales ready to respond to every inbound lead within two business hours
Notes: This is the plan for taking the FieldSense 200 Series to market, and the budget I am asking for to do it. We launch publicly on April 7, with the product page live quietly on April 4 so Elena and Jamal can put it in front of priority prospects first. The ask is $92,000 of campaign spend across April, May and June. In return, the targets I am holding myself to are 180 units sold in the first ninety days out of 250 sellable, and $750,000 of new qualified pipeline sourced by the campaign. The positioning is premium: we are selling measured accuracy in high-vibration environments, not price, and there is no launch discount. The rest of the deck is how we get there and what could stop us.

## Slide 3
01
Positioning
Who we are selling to, and the one claim we lead with

## Slide 4
Who the FieldSense 200 Is For
Process plants
Pumps, compressors, and rotating equipment
Buyer: reliability and maintenance engineers
Pain: readings that wander when the machine shakes
Systems integrators
Specify sensors across many end sites
Buyer: controls engineers
Need: clean PLC integration and documentation
Energy and midstream
Remote stations, harsh conditions
Buyer: instrumentation leads
Need: accuracy they do not have to re-verify on site
Notes: We are aiming at three kinds of buyer. The core is process plants with a lot of rotating equipment, where reliability engineers are used to sensor readings that drift as soon as vibration picks up. Second are systems integrators, who are fewer in number but specify sensors across dozens of end sites, so one win there is worth many direct deals; they care about PLC integration more than anyone. Third is energy and midstream, where stations are remote and a technician visit to re-verify a sensor is expensive. Elena and Jamal have been warming the pipeline for about six weeks already, and there are eight prospects waiting for the product page to go live. Those eight are spread across all three segments, which is some early evidence the targeting is right.

## Slide 5
The Core Claim: Accuracy Under Vibration
±0.3% accuracy in high-vibration conditions
Comparable units drift to about ±2% under the same conditions
Backed by Marcus's engineering test data
Claim wording under review by Callum; nothing external ships without his sign-off
Every asset states the test conditions alongside the number
±0.3%
Measured accuracy under high vibration, against roughly ±2% for competing units. The number customers ask about first.
Notes: Everything in the campaign hangs off one claim: the FieldSense 200 holds plus or minus 0.3 percent accuracy in high-vibration conditions that push comparable sensors out to around plus or minus 2 percent. Marcus's test data is behind it, and Elena tells me it is the first thing customers ask about in almost every discovery call, so we are leading with what buyers already care about. The risk is a customer testing it in a slightly different setup and getting a worse number. So Callum is reviewing the claims language before any external asset is final, and every place the number appears will state the conditions it was measured under. I would rather lose a little punch in the headline than defend a claim that does not hold up on someone's pump skid.

## Slide 6
Pricing and Launch Inventory
List price
$840
Per unit, single quantities
Volume price
$800
25 units and above
Launch discount
None
Premium positioning; no limited-time offer
Initial inventory
300
Units expected by March 27
Samples and demos
50
Held back for press samples and trade show demo units
Sellable at launch
250
Available to fill orders from April 7
Notes: Pricing is settled. List is $840 a unit, and the volume break at twenty-five units is $800, which Priya and Renata approved; earlier working figures of $790 are wrong and should not appear anywhere. There is no launch discount. A premium product with a discount on day one tells the market the price was never real, and we are not expecting impulse orders anyway. Devon expects 300 units built by March 27. I am holding fifty of those for press samples and demo units, which leaves 250 to sell. That is the ceiling on what the first quarter of the campaign can convert into revenue, and it is why the 90-day unit target is 180 rather than something more ambitious.

## Slide 7
02
Channels and Timeline
Where the launch shows up, and when

## Slide 8
Channel Mix at Launch
Owned
Launch email to about 4,000 contacts, April 7
Product page soft-live April 4
Spec sheet and PLC compatibility note
Paid
Paid search live April 7
LinkedIn sponsored posts to plant and controls engineers
Gulf Coast Process Expo booth, May 19–21
Earned
Press release via Cision, April 7
Contributed article in Industrial Sensor Quarterly, April 9
Press samples to four trade editors
Notes: The mix is weighted toward channels where we can measure a lead back to its source. The owned channels are cheap: the email goes to our existing list of about four thousand contacts on launch day, and the product page carries the spec sheet and, if engineering can deliver it in time, a PLC compatibility note. Paid search goes live the same day and is the biggest single line in the budget. LinkedIn lets us reach reliability and controls engineers by job title. The Gulf Coast Process Expo in May is the one trade show, chosen because a large share of our target plants are in that region. On the earned side, the press release goes out through Cision on April 7 and our contributed article in Industrial Sensor Quarterly publishes on the 9th.

## Slide 9
Launch Timeline, February to July
Feb 20
Claims language final Callum's sign-off on accuracy wording
Mar 6
Creative locked Page, email, ads, spec sheet
Mar 27
Inventory in 300 units; 50 set aside for samples and demos
Mar 30
Readiness check Inventory and materials confirmed on track
Apr 4
Product page soft-live Early link to 15 priority prospects
Apr 7
Public launch Email, paid search, press release
Apr 9
Trade article Industrial Sensor Quarterly
May 19
Gulf Coast Process Expo Three days, Houston
Jul 6
90-day review Results against targets
Notes: Working backwards from April 7. Claims language has to be final by February 20 because everything else is built on it, and creative locks on March 6 so there is time to fix anything Callum or engineering flags. Devon's inventory date of March 27 is the one I cannot move, and the readiness check the week of March 30 confirms both inventory and materials before we commit to paid media. The product page goes live on April 4 without promotion, which gives Sales a three-day head start with their priority list. The email, search and press release follow on the 7th and the article on the 9th. The expo in May is the midpoint push, and we review results against every target on July 6.

## Slide 10
Early Access and Lead Response
Jamal's list of the top 15 prospects gets the product page link on April 4
Three-day window before public launch to make early buyers feel first
Every form submission posts to Slack in real time
First response to every inbound lead within two business hours
Elena and Jamal own sales readiness; I own launch execution
2 hrs
Committed first-response time on every inbound lead, during business hours.
Notes: Two things here come from Sales and I think they are both right. First, the fifteen prospects Jamal has identified get the product page link on April 4, three days before anyone else. It costs nothing and it lets those buyers feel they were given early access, which they were. Second, the fastest way to waste this budget is to generate leads and let them sit. Every form submission on the product page will post to a Slack channel as it arrives, and Jamal has committed to a first response within two business hours. Launch execution is mine; sales readiness is Elena's and Jamal's. If inbound runs well above plan, the two-hour commitment is the first thing I will check.

## Slide 11
03
Budget and Measurement
What it costs, and how we will know it worked

## Slide 12
Campaign Budget: $92,000 Requested
Paid search
$31,000
April to June, weighted to launch month
Gulf Coast Process Expo
$26,500
Booth, freight, travel for three
LinkedIn sponsored
$12,000
Plant, reliability, and controls engineers
Video and photography
$9,500
Vibration demo video, product shots
PR and trade article
$6,000
Cision distribution, article support
Email and marketing ops
$2,000
List cleanup, form and alert setup
Contingency
$5,000
Released only with Priya's approval
Total
$92,000
Excludes 50 demo and sample units, about $24,550 at standard cost
Notes: The ask is $92,000. Paid search is the largest line at $31,000, with most of it spent in April while launch interest is highest. The expo is $26,500 all in, including freight and travel for three people. LinkedIn is $12,000, video and photography $9,500, PR distribution and article support $6,000, and email and marketing operations $2,000. I have held $5,000 as contingency that I will not spend without Priya's approval. Not in this number are the fifty sample and demo units, which carry about $24,550 at our $491 standard cost and sit in inventory rather than in the marketing budget. At 180 units, the campaign costs roughly $510 per unit sold, which comes down quickly if the pipeline converts over the following quarter.

## Slide 13
How Success Is Measured at 90 Days
Inbound form submissions
400
About $230 per lead at full spend
Sales-qualified leads
120
Accepted by Elena or Jamal
New qualified pipeline
$750K
Opportunities sourced by the campaign
Units sold
180
Of 250 sellable, about $148K in revenue
Lead response in SLA
95%
First response within two business hours
Reviewed against actuals on July 6.
Notes: These are the five numbers I will report on July 6. Four hundred inbound form submissions works out to about $230 per lead at full spend, which is reasonable for an industrial product at this price. Of those I expect a hundred and twenty to be accepted as sales-qualified by Elena or Jamal. The pipeline target is $750,000, and units sold is 180, roughly $148,000 at a blend of list and volume pricing. The fifth measure is on us rather than the market: 95 percent of leads answered inside two business hours. If we miss the volume numbers but hit pipeline, I will read that as a slower buying cycle, not a failed launch, and I will say so rather than quietly moving the targets.

## Slide 14
Launch Risks and Dependencies
Inventory
300 units by March 27
Owner: Devon
Slip means moving the launch, not launching without stock
Accuracy claim
Sign-off by February 20
Owner: Callum
Fallback: softer wording, same data
PLC compatibility
One-page note for older Siemens setups
Owners: Elena with Marcus and Sofia
Needed by April 4 or messaging changes
Demand over supply
Only 250 sellable
Backorder language ready
Second build timing from Devon
Notes: Four things could hurt the launch. Inventory is the biggest: if Devon's 300 units are not in by March 27, we move the launch date rather than generate demand we cannot fill. The accuracy claim needs Callum's sign-off by February 20; if he wants it softened, the data is the same and only the wording changes. The one I am most worried about is PLC compatibility. Several prospects run older Siemens controllers and want to know how the sensor integrates. Elena is getting a one-page note from Marcus and Sofia, and if it is not ready by April 4 we will take the question out of the messaging rather than invite it. The last risk is a good one to have: more demand than 250 units.

## Slide 15
Decisions Needed This Week
Approve the $92,000 campaign budget
Confirm April 7 as the public launch date
Confirm the split: 50 units for samples and demos, 250 sellable
Confirm the expo booth, which needs a deposit by February 20
Notes: I need four decisions this week to keep the timeline intact. The budget approval matters most, because paid search setup and the expo deposit both depend on it, and the expo booth needs its deposit by February 20 to hold the space we want. I also want April 7 confirmed as the date so Sales can start telling prospects something firmer than "spring". Priya has already indicated she is comfortable planning around Devon's inventory date. And I want the 50 and 250 split agreed now, so that no one on the sales side is surprised later that they cannot sell every unit in the building. With those four, everything else in this plan is mine to execute.